## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-05-e-SpoiledMilk
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | JS; 3/13
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | NS; 3/13
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Fail | DJ; 3/18; We don't display a message yet but when an item is out of stock the button greys out.
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | YK; 3/16
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | JC; 3/15
As an admin I want to edit the inventory so that customers can see the updated inventory. | Given I see the admin page when I login as owner then I expect to be able to add a product to the inventory. | Pass | JC; 3/15
| Given I see the admin page when I login as owner then I expect to be able to update a product in the inventory. | Pass | JC; 3/16
| Given I see the admin page when I login as owner then I expect to be able to delete a product from the inventory. | Pass | JC; 3/15
As a user I want to be able to click the shopping cart button to see my items. | Given I have an account when I press the button then I get routed to a new page. | Pass | YK; 3/13
| Given I log off when I log back on then my cart items appear again. | Pass | YK; 3/15
| Given I want to add an item when I press the increment button then the number of that specific item in my cart increases by one. | Pass | YK; 3/14
| Given I want to decrement an item when I press the decrement button then the number of that specific item in my cart decreases by one. | Pass | YK; 3/14
As a user I want to see all the milks available so that I can purchase them. | Given I have an internet connection when I go to the website then I should see a display of products. | Pass | DJ; 3/15
| Given I have an account when I click on 'Add to Cart' then the product should be added to my shopping cart. | Pass | DJ; 3/15
As a user I want to see a search bar on the e-store so that I can search for certain milks. | Given I have an account when I login then I expect to see a search bar. | Pass | NS; 3/14
As a user I want to add/remove items to/from my shopping cart so that I can edit my order. | Given there is a product I want to buy when I add a certain quantity to the cart then I should see my cart updated to have the product(s) in it. | Pass | YK; 3/14
| Given there is a product I want to remove from my cart when I select remove on that product in my cart then I see the item disappear from my cart. | Pass | YK; 3/15
As a user I want to see a login page so that I can login to the e-store and shop. | Given I have an internet connection when I go to the website then I should be able to login. | Pass | JS; 3/17
As a user I want to see a price and quantity of stock in the inventory associated with each milk so that I know the cost and how much is left. | Given that there is milk in the inventory when I search for milk then I expect the milk to have an associated price and quantity. | Pass | JS; 3/9