## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-05-e-SpoiledMilk
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | JS; 3/13 | Pass | JS; 4/1
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | NS; 3/13 | Pass | NS; 4/1
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Fail | DJ; 3/18; We don't display a message yet but when an item is out of stock the button greys out. | Pass | DJ; 4/5
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | YK; 3/16 | Pass | YK; 4/1
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | JC; 3/15 | Pass | JC; 4/1
As an admin I want to edit the inventory so that customers can see the updated inventory. | Given I see the admin page when I login as owner then I expect to be able to add a product to the inventory. | Pass | JC; 3/15 | Pass | JC; 4/3
| Given I see the admin page when I login as owner then I expect to be able to update a product in the inventory. | Pass | JC; 3/16 | Pass | JC; 4/3
| Given I see the admin page when I login as owner then I expect to be able to delete a product from the inventory. | Pass | JC; 3/15 | Pass | JC; 4/3
As a user I want to be able to click the shopping cart button to see my items. | Given I have an account when I press the shopping cart button then I get routed to the shopping cart page. | Pass | YK; 3/13 | Pass | YK; 4/4
| Given I log off when I log back on then my cart items appear again. | Pass | YK; 3/15 | Pass | YK; 4/4
| Given I want to add an item when I press the increment button then the number of that specific item in my cart increases by one. | Pass | YK; 3/14 | Pass | YK; 4/4
| Given I want to decrement an item when I press the decrement button then the number of that specific item in my cart decreases by one. | Pass | YK; 3/14 | Pass | YK; 4/4
As a user I want to see all the milks available so that I can purchase them. | Given I have an internet connection when I log in as a customer then I should see a display of products. | Pass | DJ; 3/15 | Pass | JS; 4/3
| Given I have an account when I click on 'Add to Cart' then the product should be added to my shopping cart. | Pass | DJ; 3/15 | Pass | DJ; 4/1
As a user I want to see a search bar on the e-store so that I can search for certain milks. | Given I have an account when I login then I expect to see a search bar. | Pass | NS; 3/14 | Pass | NS; 4/1
As a user I want to add/remove items to/from my shopping cart so that I can edit my order. | Given there is a product I want to buy when I add a certain quantity to the cart then I should see my cart updated to have the product(s) in it. | Pass | YK; 3/14 | Pass | YK; 4/1
| Given there is a product I want to remove from my cart when I select remove on that product in my cart then I see the item disappear from my cart. | Pass | YK; 3/15 | Pass | YK; 4/1
As a user I want to see a login page so that I can login to the e-store and shop. | Given I have an internet connection when I go to the website then I should be able to login. | Pass | JS; 3/17 | Pass | JS; 4/3
As a user I want to see a price and quantity of stock in the inventory associated with each milk so that I know the cost and how much is left. | Given that there is milk in the inventory when I search for milk then I expect the milk to have an associated price and quantity. | Pass | JS; 3/9 | Pass | JS; 4/1
As a customer I want to be able see quantities increase and decrease on the page so that I can know whats in stock or not | Given I want to increase in cart when I press add to cart then dashboard quantity decreases and cart quantity increases. |  |  | Pass | YK; 4/2
| Given I want to decrease in cart when I press - button in cart then dashboard quantity increases and cart quantity decreases. |  |  | Pass | YK; 4/2
| Given I want to increase in cart when I press + button in cart then it grays out once it reaches the quantity of available milks |  |  | Pass | YK; 4/2
As a Developer I want to store user’s passwords and allow for them to reset their passwords so that they can securely login to the e-store. | Given that a user successfully enters the e-store when they enter a username and password then I want to hash their password and store it in association with their username. |  |  | Pass | JS; 4/3
| Given that a customer logs in when they press the login button then they should have access to their own shopping cart and only their shopping cart. |  |  | Pass | JS; 4/3
| Given that a customer logs in with a wrong password when they press the login button then an error message should appear |  |  | Pass | JS; 4/3
As a developer I want to create an 'address' field so that we know where to ship the product. | Given I have a cart when I login then I expect to input my address before I make a purchase. |  |  | Pass | NS; 4/3
As a developer I want to display a total price in the shopping cart so that the customer can see how much the milks cost. | Given I have products in my cart when I return to the cart page then I expect to see the total of my purchase |  |  | Pass | JC; 4/5
As a developer I want to make items searchable in lower and uppercase so that customers can accurately find the product(s) they’re looking for. | Given I use lowercase letters when I perform a search then I expect to see a display of the milks I am searching for. |  |  | Pass | NS; 4/3
| Given I use uppercase letters when I perform a search then I expect to see a display of the milks I am searching for. |  |  | Pass | NS; 4/3
As a customer I want to be able to rate an item so that everyone else knows it’s quality. | Given I add a rating for a product when product exists then system should update and save product rating |  |  | Pass | DJ; 4/4
| Given I click on a product when product exists then I can see the rating |  |  | Pass | DJ; 4/4